## Sheet1
Task | Start Date | End Date | Duration
Personal and Family Health Management (Research & Planning) | 2024-12-01 | 2024-12-14 | 13 | 45627
Environment Setup and Initial Design | 2024-12-15 | 2024-12-21 | 6 | 45793
User Authentication | 2024-12-22 | 2024-12-28 | 6
Profile Management | 2024-12-29 | 2025-01-04 | 6
Health Status Tracking | 2025-01-05 | 2025-01-11 | 6
Family Appointment Management | 2025-01-12 | 2025-01-25 | 13
Appointment Handling Features | 2025-01-26 | 2025-02-08 | 13
Billing Integration | 2025-02-09 | 2025-02-22 | 13
Prescription-Based Purchases | 2025-02-23 | 2025-02-28 | 5
Medicine and Prescription Management | 2025-03-01 | 2025-03-14 | 13
Report Sharing | 2025-03-15 | 2025-03-21 | 6
Chat System Development | 2025-03-22 | 2025-04-04 | 13
Medical History Maintenance | 2025-04-05 | 2025-04-11 | 6
Data Security and Encryption | 2025-04-12 | 2025-04-18 | 6
Data Visualization | 2025-04-19 | 2025-04-25 | 6
Medicine Reminders and Notifications | 2025-04-26 | 2025-05-02 | 6
Comprehensive Testing and Debugging | 2025-05-03 | 2025-05-09 | 6
Optimization and Deployment | 2025-05-10 | 2025-05-16 | 6
Sprint | Week(s) | Tasks | Milestones/Features
Sprint 1 | Weeks 1-4 | - Finalize project objectives and scope. | Initial project structure, wireframes, and user journey maps.
- Develop wireframes for clinic management features.
- Define user journeys for authentication, appointment management, and report sharing.
- Set up GitHub repository and project skeleton.
Sprint 2 | Weeks 5-8 | - Develop authentication system (signup, login, logout). | Authentication system, user management APIs, initial database setup.
- Implement APIs for user management.
- Set up database for appointments and medical history.
- Build reusable UI components for authentication.
Sprint 3 | Weeks 9-12 | - Develop UI for personal and family health management forms. | User-friendly UI for health management, appointment scheduling system.
- Integrate user management APIs into frontend.
- Develop APIs for appointment scheduling and build UI for appointment calendar.
Sprint 4 | Weeks 13-16 | - Implement appointment reminders and notifications. | Appointment scheduling with reminders, prescription management system.
- Create APIs for prescription management.
- Build UI for prescription details.
- Set up medicine reminders.
Sprint 5 | Weeks 17-20 | - Develop APIs for medical report sharing. | Secure report sharing, real-time chat system for patient-clinic communication.
- Build UI for report sharing functionality.
- Set up WebSocket server for real-time communication.
- Build chat UI for patient-clinic communication.
Sprint 6 | Weeks 21-24 | - Develop APIs for medical history management. | Medical history management, data security, payment gateway, and deployment.
- Implement encryption for sensitive data.
- Set up Role-Based Access Control (RBAC).
- Build payment system APIs and integrate payment gateway (e.g., Stripe, E-Sewa).
- Conduct unit, integration, and end-to-end testing.
- Deploy the application to cloud (AWS, Azure).